## Slide 1: Twinning project ENEA – ENforcing Environmental Acquis
César Seoánez
Skopje, 22nd of April, 2016
5th Steering Committee

## Slide 2: OUTLINE
5th quarter assessment (12 January – 11 April 2016)
Programme until end of implementation (12 April – 11 August 2016)
Quarterly Report 5
Operative Side Letter 6
Outputs delivered to Steering Committee

## Slide 3: Coordination
Meetings: multiple, within missions, with stakeholders, specially industry & projects
All relevant outputs shared
E-inspection software project for Inspection Council cancelled
5th QUARTER:
Coordination with Twinning IED
Exchange of info about trainings and mutual invitation to participate
Workshop & feedback to TA Programme of Reform
2 meetings in February & March to provide detailed info and suggestions
Coordination with TA project supporting local level
No further meetings with Inspection Council, info exchanged by email

## Slide 4: Communication
Website: www.sei.gov.mk
Info about project for MoEPP’s web provided in March
Some additional visibility materials ready to be delivered (USB, bags)
5th QUARTER:
Link to web of Twinning IED included
All supporting materials, incl. inspection manual, sector factsheets & insp. checklists
2 new sections: info for industry & Frequently Asked Questions

## Slide 5: Progress vs. Work Plan
5th QUARTER:

## Slide 6: Progress vs. Work Plan
Good
5th QUARTER:

## Slide 7: Activities
5th QUARTER:
January (starting 12th )
Activity 1.2, mission 11: 1st mission info operators & communication strategy
Activity 2.1, mission 8: control & remediation of old polluted sites
Activity 1.2, mission 6: 2nd mission for check lists waste streams

## Slide 8: Activities
5th QUARTER:
February
Final feedback to draft Law for Inspection on Environment
Activity 3.1, mission 2: proposals for BPMS improvement
Steering Committee 4
Activity 2.1, mission 7: other supporting documents
Activity 1.2, mission 12: 2nd mission to finalise info operators & comm strategy

## Slide 9: Activities
5th QUARTER:
April (until 11th )
Addendum 2 endorsed
March
Activity 1.3, mission 4: 2 two-days trainings on industrial processes (regions 1 & 2)
Activity 1.3, mission 6: training based on inspection to pilot installation (region 1)
Activity 1.3, mission 5: 2 two-days trainings on industrial processes (regions 3 & 4)
Activity 1.4, mission 3: study visit to The Netherlands

## Slide 10: Activities
Main outputs
Trainings on industrial processes, and first pilot inspections
SEI - Twinning website, with new sections
Finalised sector inspection checklists & factsheets (12 sectors)
Finalised inspection manual
5th QUARTER:
Draft Law for Inspection on Environment ready for Parliament
Info for industries, including leaflet
Report & template of publicly available inspection report

## Slide 11: Activities
Main outputs
Report about inspection duties related to EU legislation on shipments of waste
5th QUARTER:
Finalised proposals for indicators to evaluate inspectorate & inspectors
Report about SEI contribution for EU reporting obligations
Report with recommendations on soil pollution prevention, control & management
SEI’s BPMS updated proposals for next steps

## Slide 12: Activities
5th QUARTER:
Other outputs
Addendum 2
Recommendations to deal with OHIS polluted site
Useful guidance docs & legislation on soil prevention & conceptual site model

## Slide 13: Participation BC experts
154 BC participants in meetings held in missions
Drafting of documents finished, trainings started
5th QUARTER:

## Slide 14: Expenditures
In 5th quarter ~ 16.5 % of activities’ budget
As planned, only 1 mission with 1 expert less
Savings in flight tickets
5th QUARTER:

## Slide 15: QUARTERLY REPORT
Draft Law  proceed fast to send to Parliament
Inspection Council should address Twinning docs sent,
to align to EU best practices
Overload in planning & reporting, evaluation of inspectors with financial penalties...
Post-Twinning cooperation between twinned Partners
Managers in SEI, MoEPP, CFCD, DEU & SEA should continue pushing for a change in Law for Insp. Supervision
Create Network of Environmental Inspectors

## Slide 16: PROGRAMME UNTIL END  TRAINING
June
April-May
April-May
April-June
July

## Slide 17: PROGRAMME UNTIL END
April
Activity 2.2, mission 6: training based on inspection to pilot installation (region 3)
Activity 1.3, mission 7: 3 one-day trainings on comm. skills & team building
Activity 3.1, mission 3: training on use of IRAM software
Steering Committee 5: 22nd April

## Slide 18: PROGRAMME UNTIL END
Updated project’s brochure
May
Activity 2.2, mission 7: training based on inspection to pilot installation (region 2)
Activity 1.3, mission 8: 3 one-day trainings on comm. skills & team building
Activity 3.1, mission 3: further work on BPMS

## Slide 19: PROGRAMME UNTIL END
Activity 3.1, mission 4: final mission BPMS
June
Activity 2.1, mission 9: first training on sampling & monitoring
Activity 2.2, mission 8: training based on inspection to pilot installation (region 4)
Activity 2.1, mission 10: second training on sampling & monitoring

## Slide 20: PROGRAMME UNTIL END
July
Activity 1.3, mission 9: four 1-day workshops to close training programme
August(until 11th)
Closure of project, final reporting
Activity 1.1, mission 6: follow-up projects
Steering Committee 6: 21st July
Closure event: 7th July

## Slide 21: OPERATIVE SIDE LETTER 6
Builds upon Addendum 2
Next week: side letter 11 (increase 1 day mission 1.3.8, to
train-the-trainers)
Explicit approval of OSL is very welcome

## Slide 22: COMMENTS TO OUTPUTS DELIVERED TO ST.C.?
3.1.2 – SEI’s BPMS updated proposals for next steps
2.1.7 – Report about inspection duties related to EU legislation on shipments of waste
1.2.12 – Info for industries, leaflet and communication strategy
1.2.12 – final version of inspection manual
1.2.12 – Report & template of publicly available inspection report
1.2.6 & 1.2.8 – final version of 12 sector & waste inspection checklists
2.1.7 – Report about SEI contribution for EU reporting obligations

## Slide 23
Thank you very much !
Благодарам многу!
blinkov_d@yahoo.com
inspection.cs@gmail.com
www.sei.gov.mk