## Slide 1: Twinning project ENEA – ENforcing Environmental Acquis
César Seoánez
Resident Twinning Adviser
Skopje, 28th of April, 2015
Activities and expected results

## Slide 2: OUTLINE
1. Why this project?
2. Key data
3. Objectives & related activities
4. Conclusions

## Slide 3: WHY THIS PROJECT?
Poor implementation & enforcement of environmental legislation
Goal:
SUSTAINABILITY 
FROM THEORY TO PRACTICE
We all need a healthy, sustainable development

## Slide 4: KEY DATA
Coordinating Partners:
1 million € , January 2015 – August 2016
Institutional diversity & approaches  best solutions

## Slide 5: OBJECTIVES & ACTIVITIES
Goal 1: Improve legal & institutional framework related to
environmental inspection
4. Recommendations for improvement of inspection system (months 4-6)
1. Legal & institutional assessment (months 1-3)
2. Suggestions for updates in key legislation (months 4-7)
3. Proposals for new Law on Inspection on Environment (months 4-9)
Sustainable  e.g. Knowledge Centre
Effective
Realistic

## Slide 6: OBJECTIVES & ACTIVITIES
Goal 2: EU approach to inspections
1. Risk matrix-based approach to planning of inspections (months 6-10)
3. Dissemination actions to stakeholders, to raise awareness (months 11-17)
Directive 2010/75/EU on Industrial Emissions
RMCEI
References:
EU IMPEL Network methodologies
2. Training & inspections with EU inspectors (months 11-17)
based on risk assessment
oriented to results

## Slide 7: OBJECTIVES & ACTIVITIES
Goal 3: Develop supporting tools
1. Website (months 2-4)
www.sei.org.mk

## Slide 8: OBJECTIVES & ACTIVITIES
Goal 3: Develop supporting tools
5. Leaflet with guidance for industries (months 13-14)
2. Proposals to improve Business Process Management System (months 5-14)
3. Manual for inspectors (months 4-7) + IPPC/BAT guidance (months 7-11)
4. Factsheets + checklists for several industrial sectors & waste streams (months 8-12)

## Slide 9: OBJECTIVES & ACTIVITIES
Goal 4: Increase capacity of state & local inspectors
1. Training Needs Assessment (month 6)
2. Training programme & materials (months 8-10)
3. Training sessions (months 11-18)
& study tours (months 5-16)
4. Design of next projects in this field (month 18)
Train the trainers

## Slide 10: CONCLUSIONS
But it is really worth it, as MS experience shows
Team work: you are important
Ambitious programme
Sustainability & Competitiveness

## Slide 11
Thank you very much!
Благодарам многу!
blinkov_d@yahoo.com
inspection.cs@gmail.com
www.sei.org.mk